## Introduction
QM-0032 /Freigegeben 15.01.2025 MS
This tool is composed by two parts:
1 - Risk Management Methodology
As start it is possible to have an overview in the Risk Management Methodology.
For more detailed information on how to use the tool just choose one of the topics in the chevrons.
You will find definitions for each option and/or the information needed on each field.
2 - Risk Management Analysis
The Risk Management Analysis table must be filled according to the methodology.
For an efficient analyis the risks must be sorted according to the Risk Factor on a descending order (just push the bottom "SORT").
This tool will generate two grafics:
a) A risk prioritization chart considering the Risk Factor
b) An Impact vs Probabiliy bubble chart. The bubble size indicates the level of control of the risk.
They are complementary and are going to give the necessary support on the risk mitigation planning.
Start Methodology
RISK MANAGEMENT TOOL
Risk Management Analysis

## 0-Methodology
Identify
Classify
Quantify
Prioritize
Plan
/ Mitigate
Monitor
Risk Management Analysis
RISK MANAGEMENT METHODOLOGY
Risk identification in terms of:
- Work Front
- Description
- Identification
Risk classification in terms of:
- Category
* Strategic
* Operational
* Financial
- Control
* Internal
* Extrnal
* Both
Risk quantification in terms of:
- Impact
- Probability
- Level of Control
Risk analisys, considering:
- Impact
- Probability
- Level of Control
Define Mitigation Technique
- Avoidance
- Transfer
- Control
- Acceptance
- Investigation
Define the planned response
Assign responsibility
Define Dead-line
Keep the risk tracking and status up-dated
Evaluate the results
Signalize issues and problems
Identify and respond to new risks
Introduction

## 1-Identify
Identify | Work Front | Assigns the risk to the work front that it belongs. The risk can be assigned to: PE, Operations, HR Process, IT, Facillity, QM, Working Safety, Supply Chain
| Risk Description | Open field to describe and detail the risk
| Risk Identification | Identify/Categorize the risks in 9 pre-defined categories, as follows: Business Continuity: Risk of causing significant unplanned amendments to effort due to business changes. Teaming: Risk that either we lack control of a sufficient amount of effort to ensure successful delivery or that critical third parties are not stable. Unproven Approach: Risk from using unproven, state-of-the-art technology or innovative business approach. Management Support: Risk that senior management support is either inadequate or distracted. User Reluctant: Risk that the people who will use the solution are not prepared or willing to use it. Regulatory: Risk that a regulator will require changes without regard to timeframes or feasibility. Scope: Risk of scope being changed without regard for plans or previous commitments. Skills: Risk of significant shortfalls in the skills of delivery team. Timeframe: Risk of causing negative business impact due to missing critical delivery dates.
Back

## 2-Classify
Classify | Category | Categorize the risks as follows: Strategy: These risks have an long term impact and require a strategic decision. Examples include technology changes, market irritations, customer changes. Operational: These risks are the most common. These occur due to operational work of the company, and include execution risks, dependency risks and relationship risks, etc. Financial: These risks have a direct financial impact. Examples include cost overruns, liquidity risk.
| Control | Define a control for the risk as follows: External: These risks are those that the company has little or no control over. Internal: These risks are completely within the control of the company. Both: These risks incorporate elements that are both Internal and External.
Back

## 3-Quantify
Quantify | Impact | This is an estimate of the overall scale of the impact following the occurrence of a risk Critical Impact; threatens overall success Extreme Impact; significant disruption to successful delivery High Impact; significant disruption to a key element of delivery over the medium and long terms Medium Impact; progress disrupted causing extensions across short and medium terms Moderate Impact; progress disrupted with manageable extensions in the short term Marginal Impact; slight exposure to disruption
| Probability | An estimate of the probability of the occurrence of a risk Extremely likely Very probable Probably Possible Unlikely High improbable
| Level of Control | The relative control which can be exerted on the probability of the risk occurring Total direct control Extensive direct control Moderate "hands-on" control Shared or Partnered control Minimal realistic control No control
| Risk Factor | Probability x Impact
Level of Control
Back

## 4-Prioritize
Back
Risk Management Analysis

## 5-Plan_Mitigate
Planned Response | Technique | The technique should be defined as follows: Avoidance: Any action that completely eliminates the risk. Transfer: Moves the responsibility for the risk to the party best placed to respond to it. Control: Identifies an action or product that becomes part of the work plan. It is monitored and reported as part of the regular performance analysis and progress reporting. Control will reduce the likelihood of a risk materializing, or if it does materialize it will reduce the potential impact. Acceptance: Is taking on the risk without putting into place a risk mitigation plan. This occurs when implementing a risk mitigation plan is impossible or not cost effective. Investigation: Recommended when no clear solution can be identified. Investigation involves undertaking further research to more accurately define the level of risk and developing a contingency plan until a mitigation plan can be developed. (*)Each technique is mostly applicable on a determined classification control. Please check in the table bellow.
| Description | Open field to give a detailed description of the planned response
Assign Responsibility | Owner | Define a responsible for the response implementation
| Due to date | Define a due to date for the implementation of the response
Control | Risk Mitigation Technique | Explanation
Internal | Control, Accept, Investigate | Develop risk mitigation responses to control these risks. If risk mitigation techniques are unavailable or cost prohibitive, or if the risk falls into the green zone on the grid, consider accepting the risk. Whenever you accept a risk, you should develop a contingency plan to respond if the risk becomes a reality. If you need more information to select a tehnique, investigate
External | Transfer, Avoid, Accept, Investigate | Transfer or avoid these risks If you can neither transfer nor avoid the risk, consider accepting it. By their nature, these risks are not within our control. Accepting these risks could result in exposure to potentially costly liabilities. Whenever you accept a risk, you should develop a contingency plan to respond if the risk becomes a reality. If you need more information to select a tehnique, investigate
Both | Transfer, Avoid, Control, Accept, Investigate | Transfer or avoid these risks, especially where control is indirect or minimal If you can neither transfer nor avoid the risk, develop risk mitigation responses to control them If risk mitigation techniques are unavailable or cost prohibitive, or the risk falls into the green zone on the grid, consider accepting it. Whenever you accept a risk, you should develop a contingency plan to respond if the risk becomes a reality. If you need more information to select a tehnique, investigate
Back

## 6-Monitor
Tracking | Date | Check-point/Meeting date
| Status | Determine the status for the planned response in the check-point date as follows: On Schedule Concluded Delayed
| Comments | Open field for any comments regarding the risk and its response
Back

## 7-Risk Management Analysis
Customer |  | Operational | Internal | Critical | Extremely likely | Total direct |  | Avoidance
Finance |  | Financial | External | Extreme | Very probable | Extensive direct |  | Transfer
Health & Safety |  | Strategic | Both | High | Probably | Moderate "hands-on" |  | Control
Human Ressource |  |  |  | Medium | Possible | Shared or partnered |  | Acceptance
Infrastructure & Buildings |  |  |  | Moderate | Unlikely | Minimal realistic |  | Investigation
IT |  |  |  | Marginal | High improbable | No control
Operations
Quality
R&D
Supply Chain
Other
Identify |  | Classify |  | Quantify |  |  |  | Planned Response |  | Assign Responsibility |  | Tracking |  |  | Ref Graf
Area | Risk Description | Category | Control | Impact | Probability | Level of Control | Risk Factor | Techique | Description | Owner | Due to date | Date | Status | Comments | IMP | Prob | LC | 1/LC
Health & Safety | Global warming leads to unnormal warm days up to 36 degress, second floor with powder coating line is not climated, temperature indoor above 40 degrees | Operational | External | High | Very probable | No control | 20 | Avoidance | Take measurements to keep temperatures indoor as low as possible and according to the law. Planning for new buildings started | COO | ongoing | 2024-01-01 | ongoing | Brownfield decided, contracting ongoing | 4 | 5 | 1 | 6
Customer | Change of buying criteria / preferences (design, technology, price points, etc.) | Strategic | Internal | Critical | Possible | No control | 18 | Investigation | Regular check of market requirements with product portfolio; ongoing innovation activity | CEO | ongoing | 2024-01-02 | ongoing | Global sales strategy meeting in Bispingen to analyse market trends | 6 | 3 | 1 | 6
Supply Chain | Global shortage of certain raw materials | Operational | External | Critical | Possible | No control | 18 | Investigation | Build up saftey stocks, check market regulary | COO | ongoing | 2024-01-03 | ongoing | Reduction of transportation through CCC reduces Risks | 6 | 3 | 1 | 6
Operations | Significant increase in transportation cost | Operational | External | High | Very probable | Moderate "hands-on" | 5 | Investigation | Investigate alternative transportation routes and options. Optimize global supply chain concept | COO | ongoing | 2024-01-04 | ongoing | Reduction of transportation through CCC reduces Risks | 4 | 5 | 4 | 3
Infrastructure & Buildings | Goods out department is located in sagging building, Risk that building is breaking | Operational | Both | Critical | Possible | Total direct | 3 | Transfer | Planning for new buildings started in order wrack existing building | COO | regular | 2024-01-05 | reacted | no workplace left in sagging building | 6 | 3 | 6 | 1
Operations | Key machinery breakdown | Operational | Both | Critical | Probably | Moderate "hands-on" | 6 | Avoidance | Regular control and maintainance | COO | regular | 2024-01-06 | ongoing | controll of every machine through a standarized controll plan and regular repair weeks, renewal of old machines | 6 | 4 | 4 | 3
Customer | Stop of investment/ loss of market | Strategic | Internal | Critical | High improbable | No control | 6 | Acceptance | Broad portfolio for different applications, global business mix | CEO | ongoing | 2024-01-07 | ongoing | regular checks on market aswell as internal strucuture | 6 | 1 | 1 | 6
Finance | Inflation will increase pricing for raw materials and components |  | External | High | Possible | Minimal realistic | 6 | Acceptance | Review inflation risk and investigate counter measures (regional sourcing etc.) | CFO | ongoing | 2024-01-08 | checked | Price increase agreed on, locally fitting to the market | 4 | 3 | 2 | 5
Health & Safety | 4th wave of pandemic COVID 19 desease which requires shut-down of one or multiple plants | Strategic | Both | Extreme | Possible | Shared or partnered | 5 | Control | Take all relevant safety instruments to avoid infections with company | COO | ongoing | 2024-01-09 | ongoing | constant check of world news and clear avoidence strategies | 5 | 3 | 3 | 4
Quality | Supplier mistakes could lead to massive reclamation | Operational | Both | Critical | Unlikely | Shared or partnered | 4 | Control | Standard checks on both sides (supplier and internal) | COO | ongoing | 2024-01-10 | checked | New quality assurence strategy implementation started | 6 | 2 | 3 | 4
Health & Safety | Vandalisim or burglary | Operational | Both | High | Possible | Shared or partnered | 4 | Control | Build up measurements to secure the stocks and buildings | COO | 2021-09-01 | 2022-10-05 | Checked | Different measurements installed, new measurements agreed on where neccassary | 4 | 3 | 3 | 4
R&D | Compensations for damages due to failure design | Operational | Internal | High | Unlikely | Minimal realistic | 4 | Control | Implement multiple quality gates in the design process | CTO | regular | 2024-01-01 | ongoing | Damage due to design faults is controlled through quality design gates during development, feedback loops as quality assurance measures, laboratory testing, and strict compliance with legal and contractual obligations | 4 | 2 | 2 | 5
Infrastructure & Buildings | Roofs in Bispingen are old and holey, water ingress could damage valuable equipment | Operational | Both | High | Possible | Moderate "hands-on" | 3 | Avoidance | Control of roof, budgeting of roof renovation | COO | regular | 2024-04-01 | ongoing | Brownfield decided, contracting ongoing | 4 | 3 | 4 | 3
Infrastructure & Buildings | Patio condition of surface is worsening, eg. forklifts could be mislead and hurt humans | Operational | Internal | High | Possible | Moderate "hands-on" | 3 | Avoidance | Control of floor, budgeting of renovation and or new building on the patio | COO | regular | 2022-09-01 | reacted | Patio partly renewd by facility management, Goods out department moved to shorten ways | 4 | 3 | 4 | 3
Human Ressource | Loss of critical talent (or low attractiveness for new talent) | Strategic | Internal | Extreme | Possible | Extensive direct | 3 | Control | "People first"-approach: long-/mid-term incentives; people-oriented culture and policies; open communication | CEO | ongoing | 2023-03-02 | ongoing | Employee poll done, different initiatives started to become more attractive as employee | 5 | 3 | 5 | 2
Infrastructure & Buildings | Break out of fire in operations | Operational | Both | Extreme | Unlikely | Moderate "hands-on" | 2.5 | Avoidance | Anti fire measurements / installation of sprinkler system | COO | 2021-12-01 | 2023-03-01 | reacted | Installation of fire alarm system in Bispingen finished | 5 | 2 | 4 | 3
Supply Chain | No supplier able to deliver to our needs | Operational | Both | High | Possible | Extensive direct | 2.4 | Avoidance | Build up competences to make or buy | COO | ongoing | 2024-01-01 | ongoing | Second source strategy for critical supplies (e.g. PCB) established, Cooperation with TH intensified, Insourcing further driven | 4 | 3 | 5 | 2
Human Ressource | Change program will not succed and employees loose faith in new structure | Strategic | Internal | High | Possible | Extensive direct | 2.4 | Control | Regular and direct interaction and involvement of employees on the change initiative |  |  | 2024-01-01 | ongoing | Improved employer communication in 2024 | 4 | 3 | 5 | 2
Health & Safety | Inadequate description of risks and behavior in operations | Operational | Internal | High | Unlikely | Extensive direct | 1.6 | Control | Regular control of all safety mechanisms and other measurements to keep up and improve safety standards | COO | regular | 2022-12-01 | checked | Organisational change in Quality Organisation initiated, regular checks done, higher focus on H&S | 4 | 2 | 5 | 2
R&D | Development of products that do not meet market needs | Strategic | Internal | Critical | Unlikely | Extensive direct | 2.4 | Investigation | Market observation, customer demand orientation, benchmarking as well as querying market needs during the development process and feedback loops with the sales department | CTO |  | 2024-01-01 | ongoing | Market and competitive analyses are conducted regularly, and competitor products and processes are systematically compared through benchmarking. Sales feedback is collected in a structured manner and integrated directly into the development process through defined feedback loops. | 6 | 2 | 5 | 2
R&D | recourse claims due to design defects | Operational | Internal | Extreme | Possible | Extensive direct | 3 | Control | ISO9001 regulations, more eyes principle during development, test steps during development, pilot series testing in the laboratory and during production | CTO/COO | regular | 2024-01-01 | ongoing | Quality gates in Designphase installed to check before launch. Quality gates are installed during the design phase, extended to the production phase, and applied throughout the production of approved products to ensure compliance with the approved standards and error-free manufacturing | 5 | 3 | 5 | 2
R&D | Problems during the development process, e.g. due to material and supplier bottlenecks or faulty deliveries - Delayed, or no, market launch | Operational | Internal | High | Unlikely | No control | 8 | Control | supplier audit-market observation | COO |  | 2024-01-01 | Ongoing | Integration of procurement department in development process as well as operations department in order to react to needs as early as possible | 4 | 2 | 1 | 6
IT | CAD system failure / ERP system failure | Operational | External | High | Possible | No control | 12 | Control | use of security sofware, backup | CFO |  | 2024-01-01 | ongoing | Update of ERP system in 2025, | 4 | 3 | 1 | 6
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
[7 empty] | 0 | [7 empty] | 0 | 0 | 1 | 0
RISK MANAGEMENT ANALYSIS
Back